Agentic PMO: Path to Product

From a working prototype to a tool a portfolio office can run on: seven gaps, five phases, one pilot.

STATUS: WORK IN PROGRESS — PROTOTYPE, NOT A FINISHED PRODUCT.  Today the prototype covers 4 of 14 standard PfMO functions fully and 7 partially (roughly 54% weighted). It proves the agent design and the workflows; it does not yet prove integrations, security or scale. Weeks are planning ranges to confirm in Phase 0, not commitments.

The seven gaps between prototype and product

1 Backend and login   2 Shared database   3 Integrations   4 Admin settings   5 Running a quarter   6 AI governance   7 Engineering basics

| Phase | What gets built | Gaps | Exit gate |
| --- | --- | --- | --- |
| Phase 0 Scope & foundations Weeks 1–3 | • Pick one business unit and 5–10 live programs; name the product owner and data owners. • Security and privacy review of what program data may go to a model. • Baseline today: time spent on status, risk and capacity reporting. | 6 | Scope signed off; security approval in hand. |
| Phase 1 Platform core Weeks 3–8 | • Hosted app split into front end and back end, with tests and a deployment pipeline. • Login, single sign-on and roles (requester, TPM, PMO lead, executive). • Shared database with history and backups; API proxy so “Generate with AI” works. • Admin settings (OKRs, scoring weights, rigor thresholds, capacity cap, TPM roster) and a first-time setup wizard. • Versioned prompts, output checks, cost limits. | 1, 2, 4, 6, 7 | Pilot users log in, run every workflow, and every change is tied to a person. |
| Phase 2 Integrations Weeks 6–11 | • Approved program creates its Jira structure. • Tempo hours feed actuals and capitalization. • Documents publish to Confluence or Glean; Slack or Teams notifications. • Start read-only; reconcile against each source system. | 3 | Portfolio numbers match source systems within an agreed tolerance. |
| Phase 3 Pilot a quarter Weeks 10–14+ | • Run beside the current process for the pilot programs. • Cut-line scenarios, mid-quarter change requests, and a logged executive override. • Bi-weekly business review views (2×2; launched, upcoming, delayed). • Log every override as feedback; tune prompts against known-good cases. | 5 | Pilot success measures met (time saved, artifact completeness, forecast accuracy, active use). |
| Phase 4 Expand After week 14 | • More business units; scoped write-back to source systems. • Remaining PfMO functions: benefits realization, change control, configurable gates. | — | Decided at the pilot review. |

Approach: layer the agents and governance workflows on the systems the organization already uses, rather than replacing them. Agents draft and advise; a named person decides, and every override is logged.

Needed to start: the pilot business unit and programs; which systems hold program status, capacity, actuals and OKRs, and who owns each; security rules for sending program data to a model; budget and headcount. Cost is not estimated here because it depends on those answers.

Code and companion one-pagers: github.com/VjRa03An/automation-agents/tree/main/agentic-pmo-suite